## Sheet1
Phase 1 — Define the API contract and internal schema (no external data yet)
Decide input fields (zip / city_state / county_state)
Decide date granularity (monthly is easiest)
Define canonical internal location schema
Define normalized time series schema
Define response JSON schema (what the frontend consumes)

Phase 2 — Build backend skeleton (no providers yet)
Choose backend framework (FastAPI is clean for APIs; Flask is simpler)
Create /health endpoint
Create /appreciation endpoint that:
validates input
returns a dummy response (hardcoded) matching schema

Phase 3 — Implement Zillow provider (first real data)
Decide how you’ll ingest Zillow data (download CSV dataset + parse locally)
Write ZillowProvider.get_timeseries(...)
Normalize to internal schema
Wire it into /appreciation?source=zillow
Add 2–3 test cases (a ZIP, a city, a county)

Phase 4 — Implement analytics (start/end selection + % change)
Implement “nearest prior month” selection rule
Compute percent change
(Optional) compute CAGR
Return values + the exact start/end points used (important for trust)

Phase 5 — Add FHFA provider and comparison mode
Implement FhfaProvider.get_timeseries(...)
Wire /appreciation?source=fhfa
Wire /appreciation?source=both
Add mismatch flagging + explainers

Phase 6 — Frontend MVP
Single page with a form
Hits backend endpoint
Displays results cleanly
Shows warning if sources disagree

Phase 7 — Hardening (what makes it real)
Caching (don’t re-parse huge datasets per request)
Input validation edge cases
Logging and debug switches
Rate limiting (basic)
Packaging/deploy notes